Project Proposal

The AI Bridge: Empowering & Bridging the Gap for Non-IT Educators and Learners

- Campaign Initiative: Hum Hain Pakistan, SDG Youth Campaign (Pilot Programme, Islamabad)

- Project Lead/Mentor: Dr. Abdul Zahid Khan, Chairperson, Department of Technology & Project Management, FMS IIUI

- Team Leads: Muhammad Sohaib Latif and Asad Naveed Akbar

- Core Team: Faculty of Management Sciences (FMS) SDG Ambassadors, organized into three teams: Awareness Campaign, Analyzing & Reporting, and Workshops & Trainings

Team Members (SDG Ambassadors)

- Asad Naveed Akbar (Team Lead)

- Bilawal Ali

- M. Tayyab

- Ibrahim bin Faisal

- Hafiz M. Hisham Khalid

- Zawar Hussain Shah

- Muhammad Sohaib Latif (Team Lead)

- Sumama Afzal

- Muhammad Atiq Qureshi

- Usman Mumtaz Abbasi

A Note on AI Collaboration & Transparency

To walk our talk on practical, ethical AI integration, this proposal was drafted and refined through a collaborative human-AI partnership. NotebookLM (Gemini) and advanced language models were utilized as assistant co-pilots to help structure the framework, align our objectives with the Hum Hain Pakistan campaign guidelines, and synthesize data metrics. Every strategy, leadership role, and milestone reflects our team's active design, vision, and commitment to real-world educational impact.

1. Executive Summary: Why We Are Doing This

When people think of artificial intelligence, they usually picture computer science labs, complex coding, or automated software engineering. But what about our classrooms in fields like Sharia and Law, Usuluddin, Arabic, Urdu, or the Social Sciences?

In these non-IT disciplines, teachers and students face a massive mountain of dense, classical, and text-heavy material. Educators spend grueling hours preparing lectures, summarizing texts, and crafting study aids, often leading to deep professional burnout.

Led by Dr. Abdul Zahid Khan and driven by the energy of our FMS SDG Ambassadors, "The AI Bridge" flips the script. We are stepping in as "AI Architects" to bring source-grounded AI tools directly into non-IT faculties. By leveraging NotebookLM, we help educators turn heavy textbooks into multi-lingual audio summaries, instant quizzes, and structured study guides without writing a single line of code.

Our FMS SDG Ambassadors, working in three coordinated teams (Awareness Campaign, Workshops & Trainings, and Analyzing & Reporting), are hitting the ground running to raise awareness, train educators, run digital quizzes, measure impact, and build a culture of sustainability across both student and teacher communities.

2. Project Leadership & Team Structure

| Role / Designation | Name / Group | Core Responsibilities & Contributions |
| --- | --- | --- |
| Project Lead & Principal Mentor | Dr. Abdul Zahid Khan (Chairperson, Dept. of Technology & Project Management) | - Overall project governance, institutional oversight, and aligning our campus efforts with the national campaign objectives. - Championing cross-departmental bridges between management sciences and non-IT faculties. - Mentoring our students on agile project management, execution discipline, and leadership. |
| Team Leads | Muhammad Sohaib Latif Asad Naveed Akbar | - Leading the overall project plan, weekly milestones, and keeping the three teams aligned and on schedule. - Acting as the main point of contact with the Project Lead and the participating departments. |
| Awareness Campaign Team | Sumama Afzal Hafiz M. Hisham Khalid Zawar Hussain Shah | - Spearheading institutional SDG literacy campaigns and awareness sessions. - Engaging both students and teachers through notice boards, social media, and the Hum Hain Pakistan digital quiz. - Driving community engagement and promoting the workshops across faculties. |
| Workshops & Trainings Team (and Cross-Department Coordination) | Muhammad Sohaib Latif Asad Naveed Akbar Muhammad Atiq Usman Mumtaz Abbasi | - Designing and delivering hands-on NotebookLM workshops and trainings for non-IT educators and learners. - Coordinating between cross-channel departments, namely FMS and the non-IT departments, for needs assessment, source material, and pilot testing. - Handling day-to-day documentation, scheduling, attendance sheets, and evidence capture. |
| Analyzing & Reporting Team | Ibrahim bin Faisal M. Tayyab Bilawal Ali | - Analyzing pre- and post-assessment surveys to measure actual comprehension gains. - Quantifying teacher time-saving metrics and operational efficiency boosts. - Designing clean data visualizations, impact dashboards, and the final report for the national exhibition. |

3. Core SDG Mapping & Targets

- SDG 4 (Quality Education): Enhances content delivery, lowers barriers for text-heavy or low-literacy learners, and directly combats teacher burnout.

- SDG 8 (Decent Work & Economic Growth): Maximizes educator efficiency, saving hours of administrative and preparation time weekly.

- SDG 10 (Reduced Inequalities): Democratizes access to modern AI tools for non-IT, linguistic, and religious/legal disciplines.

- SDG 17 (Partnerships for the Goals): Fosters collaboration between FMS student ambassadors, non-IT academic departments, parliamentary frameworks, and civil society.

4. Tangible Benefits & Measurable Impact Metrics

To ensure our project is genuinely Action-Oriented and Measurable, we are tracking four concrete outcomes:

- Teacher Time-Saving Metric: Reducing manual lesson planning and resource-formatting hours by an average of 3 to 5 hours per week per participating educator.

- Multi-Modal Output Generation: Successfully deploying verified, source-grounded assets (Audio Overviews, interactive quizzes, and summary mind maps) across at least 3 distinct non-IT courses.

- Institutional Awareness Reach: Engaging hundreds of students and teachers via our FMS SDG Ambassadors, tracking active participation in digital quizzes and awareness sessions.

- Zero-Cost Scaling: 100% reliance on existing free-tier, browser-based source-grounded AI tools, proving that high-impact innovation requires zero financial investment or heavy IT infrastructure.

5. Four-Week Implementable Plan (Week 1 to Week 4)

The plan below runs for four weeks within the Hum Hain Pakistan Quick Impact Project (QIP) execution window. In every week, all three teams work in parallel and hand work over to one another: Workshops & Trainings coordinates with the departments, Awareness Campaign drives participation, and Analyzing & Reporting measures the results.

Week 1: Project Allocation & Setup

Planning, needs assessment, and launch of awareness

| Team | Actions | Deliverables & Documentation |
| --- | --- | --- |
| Workshops & Trainings (Sohaib, Asad, Atiq, Usman) | - Coordinate with FMS and non-IT departments to identify text-heavy bottlenecks. - Collect digital source packages (textbooks, lecture notes). - Draft the Annex 1 QIP planning form and submit it for approval. | - Completed Annex 1 Project Plan. - Curated source folder. |
| Awareness Campaign (Sumama, Hisham, Zawar) | - Launch notice boards and initial awareness posts about The AI Bridge. - Prepare campaign material and the Hum Hain Pakistan digital quiz. | - Campaign posters and social media content calendar. |
| Analyzing & Reporting (Ibrahim, Tayyab, Bilawal) | - Design the digital pre-assessment surveys. - Set up the impact-tracking matrices (hours saved, materials produced). | - Pre-assessment survey and tracking sheet. |
| Mentor Oversight | - Dr. Abdul Zahid Khan approves the QIP plan and establishes cross-departmental channels. | - Approved QIP plan. |

Week 2: Notebook Architecture & Customization

Building the AI learning assets and training the educators

| Team | Actions | Deliverables & Documentation |
| --- | --- | --- |
| Workshops & Trainings (Sohaib, Asad, Atiq, Usman) | - Initialize Gemini Notebooks for target non-IT subjects and upload source texts. - Configure Audio Overviews, study guides, and multi-lingual quizzes. - Conduct the first training workshop for participating non-IT faculty. | - Discipline-specific notebooks. - First round of multi-modal teaching assets. |
| Awareness Campaign (Sumama, Hisham, Zawar) | - Promote the workshops and run the digital quiz across student and teacher communities. - Share behind-the-scenes content on social media. | - Quiz participation log. - Workshop attendance drive. |
| Analyzing & Reporting (Ibrahim, Tayyab, Bilawal) | - Collect and clean pre-assessment survey responses. - Establish the baseline for comprehension and preparation time. | - Baseline data summary. |
| Mentor Oversight | - Provide technical and structural guidance on prompt configurations. - Ensure cultural and linguistic accuracy of generated outputs. | - Verified notebook outputs. |

Week 3: Pilot Deployment & Field Testing

Hands-on use by faculty and live data collection

| Team | Actions | Deliverables & Documentation |
| --- | --- | --- |
| Workshops & Trainings (Sohaib, Asad, Atiq, Usman) | - Hand over custom notebooks to non-IT faculty members for a 5-day trial. - Provide on-the-spot support and collect feedback through the departmental channels. | - Pilot feedback logs. - Before/during/after photographs and attendance sheets. |
| Awareness Campaign (Sumama, Hisham, Zawar) | - Run mid-term awareness events and social media engagement tracks. - Capture and share early success stories from the pilot. | - Event documentation and engagement metrics. |
| Analyzing & Reporting (Ibrahim, Tayyab, Bilawal) | - Log quantitative usage metrics (hours saved, materials produced). - Run the post-assessment survey and begin comparing against the baseline. | - Usage metrics log. - Post-assessment survey results. |
| Mentor Oversight | - Oversee ethical data collection and pilot execution. - Review weekly progress reports for Monday WhatsApp submissions. | - Weekly progress report. |

Week 4: Finalization, Evaluation & Showcase

Impact analysis, submission, and preparation for the SDG Walk and national Gala

| Team | Actions | Deliverables & Documentation |
| --- | --- | --- |
| Workshops & Trainings (Sohaib, Asad, Atiq, Usman) | - Compile final documentation for institutional submission. - Hold a closing session and hand over resources to the departments. - Prepare the live demonstrations for "The AI Bridge" project stall. | - Top 3 project submission files. - Handover resource pack. |
| Awareness Campaign (Sumama, Hisham, Zawar) | - Run the closing campaign showcasing results. - Participate in the institutional SDG Walk and promote the national SDG Gala. | - Campaign wrap-up report. - SDG Walk participation. |
| Analyzing & Reporting (Ibrahim, Tayyab, Bilawal) | - Compile metric data into analytical reports and impact dashboards. - Prepare the Final QIP Evaluation Report and presentation deck for scoring out of 100. | - Final QIP Evaluation Report. - Impact dashboards and national presentation deck. |
| Mentor Oversight | - Dr. Abdul Zahid Khan chairs the institutional evaluation review. - Select and forward the institution's top 3 QIP nominations by November 14. - Support exhibition setup and celebrate student/ambassador achievements. | - Institutional nominations submitted. |

6. Why This Project Wins Nationally

- Real Interdisciplinary Collaboration: It bridges the quantitative rigor of data analysis and the operational discipline of project management with the rich cultural depth of non-IT humanities.

- Driven by Passionate Leadership: Under the direct guidance of Dr. Abdul Zahid Khan, the project gains institutional weight, accountability, and seamless execution.

- Amplified by Ambassadors: The FMS SDG Ambassadors ensure that the project is not just an isolated tech experiment, but a vibrant, campus-wide movement for sustainable education.