Quick Impact Project (QIP) Planning & Reporting Form

HHP - SDG Youth Campaign

NOTE

This form is used both to plan the QIP (Sections A–G) and to report on it after completion (Section H). It is also included in the campaign QIP presentation, so walk students through it when you explain QIPs to them.

Section A: Basic Information

Project Title: The AI Bridge: Empowering & Bridging the Gap for Non-IT Educators and Learners

School/College/University: International Islamic University, Islamabad (Faculty of Management Sciences)

Team Leader: Dr. Abdul Zahid Khan (Project Lead/Mentor); Muhammad Sohaib Latif & Asad Naveed Akbar (Team Leads) Total Volunteers in Group: 10 students

Project Duration: Four weeks (Week 1 to Week 4)

Location of Activity: International Islamic University, Islamabad (FMS and participating non-IT departments)

Section B: SDG(s) Addressed

List the SDG(s) your project addresses:

| SDG | Relevance to The AI Bridge |
| --- | --- |
| SDG 4: Quality Education | Enhances content delivery for text-heavy classical material, lowers barriers for low-literacy learners, and directly combats teacher burnout. |
| SDG 8: Decent Work & Economic Growth | Maximizes educator efficiency by saving hours of administrative and lesson-preparation time every week. |
| SDG 10: Reduced Inequalities | Democratizes access to modern AI tools for non-IT, linguistic, and religious/legal disciplines (Sharia and Law, Usuluddin, Arabic, Urdu, Social Sciences). |
| SDG 17: Partnerships for the Goals | Fosters collaboration between FMS student ambassadors, non-IT academic departments, parliamentary frameworks, and civil society. |

Section C: Problem Statement

What community issue does your project address?

Our community faces two connected challenges. First, teachers and students in non-IT disciplines such as Sharia and Law, Usuluddin, Arabic, Urdu, and the Social Sciences work with a massive volume of dense, classical, and text-heavy material. Educators spend grueling hours preparing lectures, summarizing texts, and crafting study aids, which often leads to deep professional burnout. Second, artificial intelligence is still widely seen as a subject for computer science labs and coding, so these faculties have little access to modern, source-grounded AI tools that could ease their workload. Our project tackles both problems at once by training non-IT educators and learners to use free, browser-based tools such as NotebookLM, turning heavy textbooks into multi-lingual audio summaries, instant quizzes, and structured study guides without writing a single line of code, while our SDG Ambassadors raise awareness across the campus.

Section D: Project Objectives

What do you want to achieve?

- Reduce manual lesson planning and resource-formatting time by an average of 3 to 5 hours per week for each participating educator.

- Deploy verified, source-grounded teaching assets (Audio Overviews, interactive quizzes, and summary mind maps) across at least 3 distinct non-IT courses using only free-tier tools.

- Raise awareness among hundreds of students and teachers about the SDGs and responsible, ethical use of AI in education through campaigns, workshops, and the Hum Hain Pakistan digital quiz.

Section E: Planned Activities

Describe the main activities:

1. Week 1 (Project Allocation & Setup): Coordinate with FMS and non-IT departments to identify text-heavy bottlenecks, collect digital source packages, draft and submit the Annex 1 QIP plan for approval, launch notice boards and awareness posts, and design the pre-assessment surveys and impact-tracking matrices.

2. Week 2 (Notebook Architecture & Customization): Initialize Gemini Notebooks for the target non-IT subjects, upload source texts, configure Audio Overviews, study guides, and multi-lingual quizzes, conduct the first training workshop for faculty, and run the digital quiz while the analysis team builds the baseline.

3. Week 3 (Pilot Deployment & Field Testing): Hand over the custom notebooks to non-IT faculty for a 5-day trial, provide on-the-spot support, run mid-term awareness events, log usage metrics (hours saved, materials produced), and run the post-assessment survey.

4. Week 4 (Finalization, Evaluation & Showcase): Hold a closing session and hand over resources to the departments, compile metric data into impact dashboards and the Final QIP Evaluation Report, forward the institution's top 3 QIP nominations by November 14, and prepare "The AI Bridge" stall for the institutional SDG Walk and the national SDG Gala.

Section F: Target Beneficiaries

Who will benefit from the project?

Educators and students of the non-IT departments at the participating institution (such as Sharia and Law, Usuluddin, Arabic, Urdu, and the Social Sciences), and the wider campus community (students and teachers) reached through awareness sessions, social media, and the digital quiz.

Number of Beneficiaries. (Faculty Members: ___% Students: ____%)

Section G: Resources Needed and Acquired

Resources Needed: To run The AI Bridge, the project requires:

- Free-tier, browser-based AI tools (NotebookLM / Gemini) with no paid licences

- Laptops or smartphones and a stable internet connection for training sessions

- Digital source packages (textbooks, lecture notes, and course material from non-IT departments)

- Venue and projector or screen for workshops and the closing session

- Survey tools for pre- and post-assessments and the digital quiz

- Awareness materials: posters, banners, or flyers, plus social media content to promote the workshops and the campaign

Resources Acquired: So far, the project has secured:

- Guidance and approval pathway from the Project Lead/Mentor, Dr. Abdul Zahid Khan

- A team of 10 FMS SDG Ambassadors organized into three teams

- Access to free-tier NotebookLM / Gemini tools (zero financial investment)

Section H: QIP Completion Report

Activities Conducted: Briefly describe what was done:

To be completed after Week 4. (Planned: needs assessment with FMS and non-IT departments, notebook setup and faculty workshops, a 5-day pilot trial, awareness events and the digital quiz, and impact analysis with final reporting.)

Results Achieved

| Indicator | Planned | Achieved |
| --- | --- | --- |
| Awareness sessions / events | 8 | To be achieved |
| Training workshops for non-IT faculty | 4 | To be achieved |
| Student participants (SDG Ambassadors) | 10 | Achieved |
| Non-IT courses with AI-generated assets | 3 | To be achieved |
| Educator time saved per week | 3-5 hours | To be achieved |
| Pre- and post-assessment surveys | 2 | To be achieved |
| Awareness posters | 6 | To be achieved |
| Final QIP Evaluation Report | 1 | To be achieved |

Participants

| Indicator | Planned | Achieved |
| --- | --- | --- |
| Total participants | 10 volunteers | Achieved |

Beneficiaries

| Indicator | Planned | Achieved |
| --- | --- | --- |
| Direct beneficiaries (educators and learners who attended workshops or used the AI notebooks) | To be estimated | To be achieved |
| Indirect awareness beneficiaries (reached through the campaign and digital quiz) | Hundreds (target) | To be achieved |

Other Outputs

| Output | Planned | Achieved |
| --- | --- | --- |
| Awareness materials | Posters, social media content, digital quiz | To be achieved |
| AI learning assets | Audio Overviews, quizzes, mind maps, study guides | To be achieved |
| Project documentation | Photos, attendance, report | To be achieved |

Key Achievements — Description of Change

Record the key achievements, including changes in knowledge, behaviour and practice of beneficiaries (e.g., increase in relevant SDG knowledge; actions taken by beneficiaries related to the QIP SDG(s)):

To be completed after the post-assessment survey, using the comparison with the pre-assessment baseline.

Challenges Faced

To be completed after Week 4.

Lessons Learned

To be completed after Week 4.

Sustainability Plan: How will the project impact continue after completion?

The customized notebooks, study guides, and handover resource pack will remain with the participating non-IT departments, so faculty can keep producing Audio Overviews, quizzes, and summaries at zero cost using free-tier tools. The SDG Ambassadors will continue awareness campaigns on responsible AI use and the SDGs, and the department can encourage future students to train additional faculties using the same low-cost, no-code approach.

Evidence Attached

- Before and After Photos

- Attendance Sheets

- Social Media Posts / Screenshots (if any)

- Testimonials

- News Coverage / Clippings

- Other Supporting Documents: ____________________

Team Lead (1) Signature: ____________________ Date: ____________________

Team Lead (2) Signature: ____________________ Date: ____________________

Focal Person Signature: ____________________ Date: ____________________